# Parent App — Frontend Sprint Plan (2 Weeks)

Developer: Frontend Developer (1 person, full-time)

Sprint Length: 1 week

Total Timeline: 2 weeks (Mar 18 – Mar 31)

Framework: Kotlin (Android Native) with Jetpack Compose

Platform: Android (API 26+)

Figma: [Parent App](https://www.figma.com/design/RzRLfAzFbVJD466Qzf99hh/Parent-App?node-id=0-1&p=f&t=FWwfEa14S5eml4sM-0)

Architecture: MVVM + Clean Architecture, Hilt DI, Retrofit, Room

## Sprint Overview

| Sprint | Dates | Focus | Screens |
| --- | --- | --- | --- |
| **Sprint 1** | Mar 18–24 | Setup + Login + Dashboard + Attendance + Fees | 10 screens |
| **Sprint 2** | Mar 25–31 | Leave + Communication + Notifications + Analytics + Calendar + App Store | 10 screens |

Strategy: Backend pushes APIs same-day. Frontend integrates immediately — no mock APIs needed.

## Sprint 1: Setup + Login + Dashboard + Attendance + Fees (Mar 18–24)

### Day 1 (Tue Mar 18) — Project Setup + Login

Create new Android project in Android Studio (Kotlin, Jetpack Compose, min SDK 26)

Set up project structure:

com.edmik.parentapp/
  ├── di/              (Hilt modules)
  ├── data/api/        (Retrofit interfaces)
  ├── data/model/      (API data classes)
  ├── data/repository/
  ├── data/local/      (Room DB)
  ├── domain/model/
  ├── domain/usecase/
  ├── ui/theme/        (Material 3 colors, typography)
  ├── ui/components/   (Reusable composables)
  ├── ui/navigation/   (NavHost)
  ├── ui/login/        (LoginScreen, LoginViewModel)
  └── util/

Add dependencies to build.gradle: Hilt, Retrofit, OkHttp, Moshi, Coil, Room, Navigation Compose, Material 3

Set up Material 3 theme from Figma:

Primary: `#2196F3`, PrimaryDark: `#1976D2`

Background: `#E8F4FD` → `#FFFFFF` gradient

Success: `#4CAF50`, Error: `#F44336`, Warning: `#FFC107`

Typography: Material 3 defaults (Roboto), sizes 12/14/16/20sp

Set up Retrofit + OkHttp with JWT interceptor (AuthInterceptor) + TokenAuthenticator for auto-refresh

Set up EncryptedSharedPreferences for secure token storage

Set up Hilt DI (NetworkModule, RepositoryModule)

Set up Jetpack Navigation Compose (NavHost with routes)

Build **LoginScreen** composable:

App logo, OutlinedTextField (Student ID), OutlinedTextField (Password, visualTransformation), Checkbox (Remember Me), Button (Login), TextButton (Forgot Password)

LoginViewModel: calls API, stores tokens, navigates to Dashboard

Build **ForgotPasswordScreen** (OTP flow)

Integrate with `POST /parent/login` (backend pushes Day 1)

**Commit**

### Day 2 (Wed Mar 19) — Dashboard + Profile Switcher

Build **Dashboard screen** (match Figma):

Header: Avatar + name + ID + notification bell badge

Batch selector: Blue pill + dropdown

Calendar widget: Monthly grid, event dots, nav arrows

Timeline/Schedule tabs with activity feed

Bottom navigation: Home | Analytic | Fees | Attended

Build **Student Profile Switcher** (bottom sheet)

Build reusable composables: CalendarWidget, ActivityCard, BottomNavBar

Integrate with `GET /parent/dashboard` + `GET /parent/students`

**Commit**

### Day 3 (Thu Mar 20) — Attendance (All Views)

Build **Attendance — Class View** (match Figma):

Class/Subject toggle tabs

Today's Status card (green Present / red Absent)

Donut chart (present/absent/leave, center=total)

Attendance % with "Including leave" toggle

Low Attendance Alert banner (pink bg, warning icon)

Build **Attendance — Subject View** (match Figma):

Today's Schedule cards (side-by-side, per subject)

Subject dropdown accordion

Per-subject donut chart

Build **Attendance Calendar View** (monthly colored cells)

Build **Semi-circle Gauge** variant

Build reusable composables: DonutChart (MPAndroidChart or Vico), GaugeChart, AlertBanner

Integrate with all 5 `GET /parent/attendance/*` endpoints

**Commit**

### Day 4 (Fri Mar 21) — Fees (All Screens)

Build **Fee List screen:**

Summary card (Total / Paid / Pending)

Fee cards with status badges (green/amber/red)

Pay Now + Download Receipt buttons

Build **Fee Detail + Payment screen:**

Breakdown, payment history, restructure history

Razorpay Android SDK integration (`com.razorpay:checkout:1.6.33`)

Build **Payment Result screen** (success/failure)

Integrate with all 6 `GET/POST /parent/fees/*` endpoints

Test payment with Razorpay sandbox

**Commit**

### Day 5 (Sat Mar 22) — Polish + Bug Fixes

Test full flow: Login → Dashboard → Attendance → Fees → Pay

Fix integration bugs

Add loading spinners, error states, empty states

Add pull-to-refresh on list screens

Test on physical Android device

**Commit & push**

### Sprint 1 Deliverables: 10 Screens

| # | Screen | Figma? |
| --- | --- | --- |
| 1 | Login | No — use spec wireframe |
| 2 | Forgot Password | No — use spec wireframe |
| 3 | Dashboard (Home) | ✓ Match Figma |
| 4 | Dashboard (Schedule tab) | ✓ Match Figma |
| 5 | Student Profile Switcher | No — bottom sheet |
| 6 | Attendance — Class View | ✓ Match Figma |
| 7 | Attendance — Subject View | ✓ Match Figma |
| 8 | Attendance — Calendar | ✓ Reuse calendar widget |
| 9 | Fee List | No — use spec wireframe |
| 10 | Fee Detail + Payment + Result | No — use spec wireframe |

## Sprint 2: Leave + Communication + Notifications + Analytics + Calendar + App Store (Mar 25–31)

### Day 1 (Tue Mar 25) — Leave Management (3 screens)

Build **Apply Leave screen:**

Leave type dropdown

Date range picker

Reason text area (min 10 chars)

Attach document (camera/gallery, max 5MB)

Submit with confirmation dialog

Build **Leave History screen:**

Filter tabs: All / Pending / Approved / Rejected

Leave cards with status badges

Build **Leave Detail screen:**

Full details + status timeline

Cancel button (if SUBMITTED)

Integrate with 5 `/parent/leave/*` endpoints

**Commit**

### Day 2 (Wed Mar 26) — Communication (3 screens)

Build **Conversations List screen:**

Teacher/admin name + last message + timestamp + unread count

New Message FAB, search bar

Build **Message Thread screen:**

Chat bubbles (parent=right, teacher=left)

Text input + send + attach image

Read receipts, auto-scroll

Build **Announcements screen:**

List with title, date, preview

Full view with attachments

Acknowledge button

Integrate with 6 `/parent/messages/*` + `/parent/announcements/*` endpoints

**Commit**

### Day 3 (Thu Mar 27) — Notifications + Analytics

Build **Notification Centre:**

Scrollable list, category icons, read/unread

Deep-link on tap, Mark All Read, pull-to-refresh

Badge on bottom nav + app icon

Build **Notification Preferences:**

Per-category toggles, quiet hours picker

Set up FCM: request permission → get token → register device → handle taps

Build **Analytics Dashboard:**

Performance summary, subject cards with trends

Weak areas + recommendations

Progress trend line chart

Integrate with `/parent/notifications/*` + `/pulse/analytics/parent/dashboard`

**Commit**

### Day 4 (Fri Mar 28) — Calendar + Subject Detail + Offline

Build **Academic Calendar:**

Monthly view, colored dots by event type

Tap day → event list

Build **Analytics Subject Detail:**

Score history, trend chart, class avg comparison

Implement offline support:

Cache dashboard + attendance locally

"Last updated X min ago" banner when offline

Queue leave/messages for sync

Integrate with remaining endpoints

**Commit**

### Day 5 (Sat Mar 29) — Testing + App Store Prep

Test ALL 20 screens end-to-end on physical device

Test on low-end Android (2GB RAM, 4G)

Test 150% font scaling

Fix critical bugs

Generate signed Android APK/AAB (release keystore)

App screenshots (5 screens) for Play Store

Play Store listing (title, description)

Submit to Google Play (internal testing track)

**Commit & push — DONE**

### Sprint 2 Deliverables: 10 Screens

| # | Screen | Figma? |
| --- | --- | --- |
| 11 | Apply Leave | No — use spec wireframe |
| 12 | Leave History | No — use spec wireframe |
| 13 | Leave Detail | No — use spec wireframe |
| 14 | Conversations List | No — use spec wireframe |
| 15 | Message Thread | No — use spec wireframe |
| 16 | Announcements | No — use spec wireframe |
| 17 | Notification Centre | No — use spec wireframe |
| 18 | Notification Preferences | No — use spec wireframe |
| 19 | Analytics Dashboard | No — use spec wireframe |
| 20 | Academic Calendar | No — reuse calendar widget |

## 2-Week Timeline (Both Teams)

WEEK 1 (Mar 18-22)
═══════════════════════════════════════════════════════
Day 1 │ Backend: Auth+Dashboard API     │ Frontend: Setup+Login
Day 2 │ Backend: 5 Attendance APIs      │ Frontend: Dashboard
Day 3 │ Backend: 6 Fees APIs            │ Frontend: Attendance (all views)
Day 4 │ Backend: Multi-Student+Security  │ Frontend: Fees+Payment
Day 5 │ Backend: Testing+Fixes          │ Frontend: Polish+Bug fixes

WEEK 2 (Mar 25-29)
═══════════════════════════════════════════════════════
Day 6 │ Backend: 5 Leave APIs           │ Frontend: Leave (3 screens)
Day 7 │ Backend: 6 Communication APIs   │ Frontend: Communication (3 screens)
Day 8 │ Backend: 7 Notification APIs    │ Frontend: Notifications+Analytics
Day 9 │ Backend: Analytics+Calendar     │ Frontend: Calendar+Offline+Subject
Day 10│ Backend: Final testing          │ Frontend: Testing+App Store submit

Backend delivers ~4 endpoints/day → Frontend builds ~2 screens/day → Both finish Day 10.

## Risk Mitigation

| Risk | Mitigation |
| --- | --- |
| Backend behind schedule | Frontend uses mock data for 1 day, catches up next day |
| Figma designs missing for 12 screens | Use wireframes from Frontend Spec + design system colors from Figma |
| Razorpay integration issues | Use sandbox mode, allocate Day 5 buffer |
| FCM setup delays | Notifications screen works without push (in-app list only) |
| App Store rejection | Submit to internal track first, fix issues in v1.0.1 |